## DEVELOPMENT LOG
DEVELOPMENT LOG
PROJECT NAME |  | Python Web Scraping
PROJECT ID |  | -
PROJECT MANAGER |  | Jayanth G S
DOCUMENT VERSION |  | 6
PROJECT START DATE |  | 2020-06-15
PROJECT END DATE |  | 2020-07-31
SL NO | FEATURE NAME | VERSION 1 LINK | VERSION 1 CREATION DATE | VERSION 2 LINK | VERSION 2 CREATION DATE | VERSION CHANGE DESCRIPTION | DEVELOPMENT STATUS | REVIEW STATUS | COMMENTS
1 | Webscraping of college details |  | 2020-07-06 |  | 2020-07-07 | Solved some errors | Completed | Reviewed | Explored the structure of the website
2 | Scraping the data and create a CSV file |  | 2020-07-08 |  | 2020-07-11 | Added more attributes | Completed | Reviewed | More information is added
3 | Data of each college is extracted |  | 2020-07-13 |  | - | - | Completed | Reviewed | -
4 | Updating the CSV file |  | 2020-07-17 |  | - | - | Completed | Reviewed | -
5 | Visualization of data |  | 2020-07-18 |  | - | - | Completed | Reviewed | Using Seaborn and Matplotlib
6 | Visualization of data |  | 2020-07-21 | https://github.com/abhi7585/CC-Internship | - | - | Completed | Reviewed | Using PowerBI