## Sheet1
PROJECT PLAN FOR EXECUTION PHASE
PROJECT NAME | Python webscrapping
PROJECT MANAGER | JAYANTH G S |  | EXECUTION PHASE START DATE: |  | 2020-07-06
PROJECT DELIVERABLE | Cloud Counselage |  | EXECUTION PHASE END DATE: |  | 2020-07-27
PROJECT SCOPE | College Details
PROJECT START DATE | 2020-06-15
PROJECT END DATE | 2020-07-31
OVERALL PROGRESS | Completed
PARENT FEATURE | FEATURES | REQUIRED TIME (IN HRS) | START DATE | END DATE | DURATION IN DAYS | STATUS
1. Initiation | 1.1 Understand the business problem |  | 2020-06-16 | 2020-06-17 | 2 | COMPLETED
| 1.2 Understand the problem statement |  | 2020-06-17 | 2020-06-17 | 1 | COMPLETED
2. Planning | 2.1 Create Project charter |  | 2020-06-22 | 2020-06-24 | 3 | COMPLETED
| 2.2 Create SRS |  | 2020-06-23 | 2020-06-25 | 3 | COMPLETED
| 2.3 Create a design model |  | 2020-06-27 | 2020-06-27 | 1 | COMPLETED
3. Execution | 3.1 Understanding the structure of the website |  | 2020-07-06 | 2020-07-07 | 2 | COMPLETED
| 3.2 Perform Data Extraction |  | 2020-07-08 | 2020-07-13 | 6 | COMPLETED
| 3.3 Data storage |  | 2020-07-14 | 2020-07-16 | 3 | COMPLETED
| 3.4 Data Visualization |  | 2020-07-17 | 2020-07-24 | 8 | COMPLETED
| 3.5 Update RAID log and Development log |  | 2020-07-07 | 2020-07-30 | 23 | COMPLETED
4. Testing | Manual testing |  | 2020-07-28 | 2020-07-29 | 2 | COMPLETED
5. Closure | --- |  | 2020-07-29 | 2020-07-29 | 1 | COMPLETED